## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Light
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Riku Nakano
Project start date: | 2024-09-10 |  |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling increment: | 5 | time axis 2024-09-15 to 2024-11-09
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-09-15 to 2024-11-09
Project development
Project charter | Goal | Name | 25% | 2024-09-10 | 3
Research | Milestone |  |  | 2024-09-15 | 1 | bar: 2024-09-15
Projections | Low Risk |  | 50% | 2024-09-07 | 10
Stakeholders | Milestone |  |  | 2024-09-30 | 1 | bar: 2024-09-30
Review | Med Risk |  | 10% | 2024-09-16 | 6
Contracts
Proposals | High Risk |  | 60% | 2024-09-16 | 13
Document review | On Track |  | 50% | 2024-09-18 | 9
Bid date | Low Risk |  | 33% | 2024-09-23 | 11
Award date | Milestone |  |  | 2024-09-25 | 1 | bar: 2024-09-25
Finalize |  |  |  | 2024-09-26 | 24
Design
Feasibility study | On Track |  |  | 2024-09-25 | 4
Submit permit applications | Med Risk |  |  | 2024-09-28 | 14
Design proposal | On Track |  |  | 2024-10-13 | 6
Materials | Goal |  |  | 2024-10-17 | 3 | 2024-10-17: 2; 2024-10-18: 2; 2024-10-19: 2
Equipment | Low Risk |  |  | 2024-09-16 | 19
Testing
Environment |  |  |  | 2024-10-20 | 15
System test |  |  |  | 2024-11-03 | 5
Issues/bugs | Milestone |  |  | 2024-12-15 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT: Romulus I
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Will Rimicci, Austin Chappell, Wolfgang Ploch, August Bresnaider
Project start date: | 2024-08-27 | 2024-08-27 |  |  |  | August | [6 empty] | September | [27 empty] | October
ROMULUS-I | 0 | time axis 2024-08-27 to 2024-10-21
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Confirm ALU Ops | On Track | All | 100% | 2024-08-27 | 6
Confirm ISA | On Track | All | 100% | 2024-09-01 | 1
Confirm PC Timing | On Track | All | 0% | 2024-09-01 | 1
Confirm Control Signals Logic | On Track | All | 0% | 2024-09-01 | 5
Code Simulator | On Track | August | 0% | 2024-09-02 | 3
Write Test Programs | On Track | Austin, Will | 0% | 2024-09-05 | 3
Generate High Level Schematic | On Track | Wolfgang | 0% | 2024-09-02 | 7
Create Low Level Schematic | On Track | All | 0% | 2024-09-02 | 11
Design PCB(s) | On Track | Austin, Will, Wolfgang | 0% | 2024-09-13 | 4
Order Parts | On Track | All | 0% | 2024-09-13 | 2
Design EEPROM Programmer | On Track | Will, Wolfgang | 0% | 2024-09-07 | 4
Code EEPROM Programmer | On Track | August, Austin | 0% | 2024-09-10 | 2
Synthesize in Verilog | On Track | August, Wolfgang | 0% | 2024-09-09 | 7
Test on FPGA | Low Risk | August | 0% | 2024-09-15 | 1
Determine Language Syntax | On Track | August, Austin | 0% | 2024-09-07 | 5
Create ANTLR Grammar | On Track | August, Austin | 0% | 2024-09-12 | 7
Create ANTLR AST | On Track | August, Austin | 0% | 2024-09-19 | 7
Create Semantic Analyzer | On Track | August, Austin | 0% | 2024-09-25 | 7
Create Code Generator | On Track | August, Austin | 0% | 2024-10-02 | 7
Fab PCB | On Track | Wolfgang | 0% | 2024-09-27 | 2
Test PCB | On Track | August, Austin | 0% | 2024-10-04 | 7
Determine Peripherals | On Track | All | 0% | 2024-10-11 | 7
Low Level Peripheral Schematics | On Track | All | 0% | 2024-10-16 | 5
Design Peripheral PCBs | On Track | Will, Wolfgang | 0% | 2024-10-21 | 21
Order Peripheral Parts | On Track | All | 0% | 2024-10-21 | 21
Solder Peripheral(s) | On Track | Wolfgang | 0% | 2024-10-28 | 21
Measure Power Consumption | On Track | Wolfgang | 0% | 2024-10-11 | 1
Design Power Supply | On Track | Will, Wolfgang | 0% | 2024-10-12 | 1
Fab Power Supply | On Track | Will, Wolfgang | 0% | 2024-10-13 | 1

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2024-09-10 |  |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling increment: | 5 | time axis 2024-09-15 to 2024-11-09
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-09-15 to 2024-11-09
TITLE 1
Task 1 | Goal | Name | 25% | 2024-09-10 | 3
Task 2 | Milestone |  |  | 2024-09-15 | 1 | bar: 2024-09-15
Task 3 | Low Risk |  | 50% | 2024-09-07 | 10
Task 4 | Milestone |  |  | 2024-09-30 | 1 | bar: 2024-09-30
Task 5 | Med Risk |  | 10% | 2024-09-16 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-09-16 | 13
Task 2 | On Track |  | 50% | 2024-09-18 | 9
Task 3 | Low Risk |  | 33% | 2024-09-23 | 11
Task 4 | Milestone |  |  | 2024-09-25 | 1 | bar: 2024-09-25
Task 5 |  |  |  | 2024-09-26 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-09-25 | 4
Task 2 | Med Risk |  |  | 2024-09-28 | 14
Task 3 | On Track |  |  | 2024-10-13 | 6
Task 4 | Goal |  |  | 2024-10-17 | 3 | 2024-10-17: 2; 2024-10-18: 2; 2024-10-19: 2
Task 5 | Low Risk |  |  | 2024-09-16 | 19
TITLE 4
Task 1 |  |  |  | 2024-10-20 | 15
Task 2 |  |  |  | 2024-11-03 | 5
Task 3 | Milestone |  |  | 2024-12-15 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one